Veer Project Plan

Course: Computer Science Senior Design I

Advisor: Dr. Jillian Aurisano

Team: Grady Algire, Brady Cooper, Briar Elliot, Dominic Rowland, Aiden Ward

Assignments #5 and #6 | October 28, 2026

Project goal: Convert driver speech into routing constraints for hands-free navigation

Names and IDs match D0 to D2. T = task, M = milestone, B = protected buffer block, RK = risk.

# 1. Task List (Assignment #5)

T1. Develop the C1 Mobile Navigation app shell: destination entry, map, and turn-by-turn guidance (I1b, I1c). Owner: Grady Algire.

T2. Develop the C1 Mobile Navigation trip state machine and its I2/I4 calls. Owner: Grady Algire.

T3. Develop the Configuration component and GET /config/client. Owner: Grady Algire.

T4. Develop the backend on Render: Express, PostgreSQL, and CI. Owner: Grady Algire.

T5. Test the full Veer system end to end on supervised test drives (US-01 to US-05). Owner: Grady Algire.

T6. Obtain written proof of the E2 AI Provider no-retention setting and pick the audio format (G-03, G-08). Owner: Briar Elliot.

T7. Develop the C2 Speech Understanding I2 endpoint with E2 transcription. Owner: Briar Elliot.

T8. Develop C2 Speech Understanding constraint extraction and allow-list check. Owner: Briar Elliot.

T9. Develop C2 Speech Understanding "okay" / "no" replies and short confirmations. Owner: Briar Elliot.

T10. Validate C2 Speech Understanding accuracy with accent samples (US-05). Owner: Briar Elliot.

T11. Research E3 Google Maps Platform terms for in-app guidance and get API keys (G-04). Owner: Brady Cooper.

T12. Develop the C3 Route Planning I4 endpoint and E3 routes client. Owner: Brady Cooper.

T13. Develop C3 Route Planning food and business stop insertion (US-01). Owner: Brady Cooper.

T14. Develop C3 Route Planning avoid highways and tolls, and the next route on "no". Owner: Brady Cooper.

T15. Test C3 Route Planning edge cases EC-09 to EC-12. Owner: Brady Cooper.

T16. Investigate E4 Weather Provider data and propose rain settings (G-02). Owner: Dominic Rowland.

T17. Develop the E4 Weather Provider client and rain avoidance in C3 (US-02). Owner: Dominic Rowland.

T18. Investigate on-device "Veer, stop listening" and a C1 Mobile Navigation foreground service (G-01, G-06). Owner: Dominic Rowland.

T19. Develop C1 Mobile Navigation mic control, listening indicator, and one-tap mute (I1a, US-04). Owner: Dominic Rowland.

T20. Develop the Notifications component: trip notice, driver notices, and budget alerts. Owner: Dominic Rowland.

T21. Develop the C4 Usage Monitor database tables and retention job (G-05). Owner: Aiden Ward.

T22. Develop C4 Usage Monitor checkQuota and recordUsage (I7 to I9). Owner: Aiden Ward.

T23. Develop the Authentication component: register, refresh, and Keystore storage. Owner: Aiden Ward.

T24. Develop the Logging component with redaction. Owner: Aiden Ward.

T25. Develop the C4 Usage Monitor usage report and spending caps (US-03, G-07). Owner: Aiden Ward.

# 2. Milestones List (Assignment #6)

| ID | Milestone | Date | Shows | How verified | By whom | Status |
| --- | --- | --- | --- | --- | --- | --- |
| M-01 | Team roster and signed team contract | Sep 3 | Team formed; roles agreed. | Submitted on Canvas. | Instructor | Complete |
| M-02 | Topic statement, bios, and reflective essay | Sep 18 | Project idea; member skills. | Files in repo; graded. | Advisor, instructor | Complete |
| M-03 | Advisor named and constraints essay | Sep 18 | Advisor; design constraints. | File in repo; graded. | Advisor, instructor | Complete |
| M-04 | User stories and use cases | Sep 26 | US-01 to US-05. | File in repo; graded. | Advisor, instructor | Complete |
| M-05 | Design D0 high-level design | Oct 2 | Components, interfaces, owners. | Files in repo; graded. | Advisor, instructor | Complete |
| M-06 | Design D1 detailed design part 1 | Oct 8 | C2 and C3 design, tech stack. | Files in repo; graded. | Advisor, instructor | Complete |
| M-07 | Design D2 detailed design part 2 and peer review | Oct 14 | C1, C4, glue design; edge cases. | Files in repo; peer review. | Peer group, advisor | Complete |
| M-08 | Task timeline and effort matrix (this document) | Oct 28 | Tasks, dates, effort, risks. | Tasklist.md and Planning/ in repo. | Advisor, instructor | Submitted |
| M-09 | Requirements and technical specification documents | Nov 4 | Requirements traced to design. | Documents submitted. | Advisor, instructor | Planned |
| M-10 | Test plan draft | Nov 11 | How each requirement is tested. | Draft submitted. | Advisor, instructor | Planned |
| M-11 | Ethics and responsible-use statement | Nov 18 | Privacy, licensing, AI use. | Statement submitted. | Advisor, instructor | Planned |
| M-12 | Research gaps closed (G-01 to G-04, G-06, G-08) | Nov 24 | Open design questions answered. | Findings in repo; D2 gaps closed. | Advisor; Team | Planned |
| M-13 | Presentation draft and advisor feedback | Nov 25 | Slides and demo plan. | Advisor reviews draft. | Advisor | Planned |
| M-14 | Team oral presentation | Dec 2 | Topic, design, and plan. | Presented in class. | Instructor, class | Planned |
| M-15 | Backend live on Render with C4 tables | Dec 2 | Backend and C4 tables live. | Health check passes; CI green. | Team | Planned |
| M-16 | Design report, design notebook, team and self assessment | Dec 9 | Fall progress against this plan. | Report, notebook, assessments. | Advisor, instructor | Planned |
| M-17 | Spring platform ready: auth and logging | Feb 1 | Login and redacted logs work. | Scripted smoke test passes. | Team | Planned |
| M-18 | Speech-to-constraint demo | Feb 12 | Speech becomes a valid constraint. | 8 of 10 test phrases correct. | Team; advisor | Planned |
| M-19 | Route proposal demo (US-01) | Feb 15 | Phone gets a route with a food stop. | Live demo on a phone. | Team; advisor | Planned |
| M-20 | Alpha: full voice loop in a parked car | Mar 3 | Full voice loop; mute under 1 s. | Timed demo in a parked car; video. | Team; advisor | Planned |
| M-21 | Beta: accuracy and edge cases checked | Mar 15 | Accent and edge-case tests pass. | Test reports in repo. | Team; advisor | Planned |
| M-22 | Usage report and caps enforced (US-03) | Mar 16 | Usage report and budget alerts work. | Test budget hits 80 and 100 percent. | Team | Planned |
| M-23 | Feature freeze after test drives | Apr 2 | Every scope item works on real drives. | Drive log, each story pass/fail. | Team; advisor | Planned |
| M-24 | Final demo build tagged | Apr 8 | Expo build ready. | v1.0 tag installs on a clean phone. | Team; advisor | Planned |
| M-25 | Senior Design Expo demo | Apr 15 | Live demo for visitors and judges. | Expo judging. | Judges, advisor | Planned |

# 3. Table 1: Timeline (Assignment #6)

Buffer is 20 percent per task, from Work done to Completion. Yellow rows (B) are protected blocks before major milestones. CP = critical path. No work is planned over Thanksgiving, finals, winter break, or spring break.

| ID | Task or milestone | Owner | Start | Work done | Buffer | Completion | Depends on | CP / Risk |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T4 | Develop the backend on Render: Express, PostgreSQL, and CI | Grady | Nov 2 | Nov 10 | 2 d | Nov 12 | None | RK-05 |
| T6 | Obtain written proof of the E2 AI Provider no-retention setting and pick the audio format (G-03, G-08) | Briar | Nov 2 | Nov 9 | 2 d | Nov 11 | None | RK-01 |
| T11 | Research E3 Google Maps Platform terms for in-app guidance and get API keys (G-04) | Brady | Nov 2 | Nov 9 | 2 d | Nov 11 | None | RK-02 |
| T18 | Investigate on-device "Veer, stop listening" and a C1 Mobile Navigation foreground service (G-01, G-06) | Dominic | Nov 2 | Nov 9 | 2 d | Nov 11 | None | RK-03 |
| M-09 | Milestone: Requirements and technical specification documents |  |  |  |  | Nov 4 |  |  |
| M-10 | Milestone: Test plan draft |  |  |  |  | Nov 11 |  |  |
| T16 | Investigate E4 Weather Provider data and propose rain settings (G-02) | Dominic | Nov 12 | Nov 19 | 2 d | Nov 23 | None | RK-09 |
| T3 | Develop the Configuration component and GET /config/client | Grady | Nov 13 | Nov 23 | 2 d | Nov 30 | T4 |  |
| T21 | Develop the C4 Usage Monitor database tables and retention job (G-05) | Aiden | Nov 13 | Nov 24 | 2 d | Dec 1 | T4 |  |
| M-11 | Milestone: Ethics and responsible-use statement |  |  |  |  | Nov 18 |  |  |
| M-12 | Milestone: Research gaps closed (G-01 to G-04, G-06, G-08) |  |  |  |  | Nov 24 | T18, T6, T11, T16 |  |
| M-13 | Milestone: Presentation draft and advisor feedback |  |  |  |  | Nov 25 |  |  |
| B-01 | Protected block before M-16 | Team | Dec 2 | Dec 8 | 5 d | Dec 8 |  |  |
| M-14 | Milestone: Team oral presentation |  |  |  |  | Dec 2 |  |  |
| M-15 | Milestone: Backend live on Render with C4 tables |  |  |  |  | Dec 2 | T4, T21 |  |
| M-16 | Milestone: Design report, design notebook, team and self assessment |  |  |  |  | Dec 9 | T21, T3, T18 |  |
| T1 | Develop the C1 Mobile Navigation app shell: destination entry, map, and turn-by-turn guidance (I1b, I1c) | Grady | Jan 11 | Jan 22 | 2 d | Jan 26 | T18, T11 | CP RK-02 |
| T7 | Develop the C2 Speech Understanding I2 endpoint with E2 transcription | Briar | Jan 11 | Jan 22 | 2 d | Jan 26 | T6, T4 | RK-01, RK-04 |
| T12 | Develop the C3 Route Planning I4 endpoint and E3 routes client | Brady | Jan 11 | Jan 25 | 2 d | Jan 27 | T11, T4 | RK-02 |
| T17 | Develop the E4 Weather Provider client and rain avoidance in C3 (US-02) | Dominic | Jan 11 | Jan 25 | 2 d | Jan 27 | T16 | RK-09 |
| T23 | Develop the Authentication component: register, refresh, and Keystore storage | Aiden | Jan 11 | Jan 20 | 2 d | Jan 22 | T4 |  |
| T24 | Develop the Logging component with redaction | Aiden | Jan 25 | Jan 28 | 1 d | Jan 29 | T3 |  |
| T2 | Develop the C1 Mobile Navigation trip state machine and its I2/I4 calls | Grady | Jan 27 | Feb 9 | 2 d | Feb 11 | T1, T23 | CP RK-08 |
| T8 | Develop C2 Speech Understanding constraint extraction and allow-list check | Briar | Jan 27 | Feb 9 | 2 d | Feb 11 | T7 | RK-04 |
| T13 | Develop C3 Route Planning food and business stop insertion (US-01) | Brady | Jan 28 | Feb 10 | 2 d | Feb 12 | T12 |  |
| T22 | Develop C4 Usage Monitor checkQuota and recordUsage (I7 to I9) | Aiden | Feb 1 | Feb 11 | 2 d | Feb 15 | T21, T3 | RK-05 |
| M-17 | Milestone: Spring platform ready: auth and logging |  |  |  |  | Feb 1 | T24, T23 |  |
| T9 | Develop C2 Speech Understanding "okay" / "no" replies and short confirmations | Briar | Feb 12 | Feb 19 | 2 d | Feb 23 | T8 |  |
| T19 | Develop C1 Mobile Navigation mic control, listening indicator, and one-tap mute (I1a, US-04) | Dominic | Feb 12 | Feb 22 | 2 d | Feb 24 | T2 | CP RK-03 |
| M-18 | Milestone: Speech-to-constraint demo |  |  |  |  | Feb 12 | T7, T8 |  |
| T14 | Develop C3 Route Planning avoid highways and tolls, and the next route on "no" | Brady | Feb 15 | Feb 23 | 2 d | Feb 25 | T13 |  |
| M-19 | Milestone: Route proposal demo (US-01) |  |  |  |  | Feb 15 | T13, T2 |  |
| T25 | Develop the C4 Usage Monitor usage report and spending caps (US-03, G-07) | Aiden | Feb 16 | Feb 23 | 2 d | Feb 25 | T22, T23 | RK-05 |
| T10 | Validate C2 Speech Understanding accuracy with accent samples (US-05) | Briar | Feb 24 | Mar 3 | 2 d | Mar 5 | T9 | RK-04 |
| T20 | Develop the Notifications component: trip notice, driver notices, and budget alerts | Dominic | Feb 25 | Mar 4 | 2 d | Mar 15 | T22, T1 | CP RK-03 |
| B-02 | Protected block before M-20 | Team | Feb 26 | Mar 2 | 3 d | Mar 2 |  |  |
| T15 | Test C3 Route Planning edge cases EC-09 to EC-12 | Brady | Feb 26 | Mar 4 | 1 d | Mar 5 | T14, T17 |  |
| M-20 | Milestone: Alpha: full voice loop in a parked car |  |  |  |  | Mar 3 | T19, T9, T14, T17, T22 |  |
| M-21 | Milestone: Beta: accuracy and edge cases checked |  |  |  |  | Mar 15 | T10, T15, T24 |  |
| T5 | Test the full Veer system end to end on supervised test drives (US-01 to US-05) | Team | Mar 16 | Mar 25 | 2 d | Mar 29 | T19, T9, T14, T17, T24, T20, T25, M-20 | CP RK-08, RK-09 |
| M-22 | Milestone: Usage report and caps enforced (US-03) |  |  |  |  | Mar 16 | T20, T25 |  |
| B-03 | Protected block before M-23 | Team | Mar 30 | Apr 1 | 3 d | Apr 1 |  |  |
| M-23 | Milestone: Feature freeze after test drives |  |  |  |  | Apr 2 | T5 |  |
| B-04 | Protected block before M-24 | Team | Apr 5 | Apr 7 | 3 d | Apr 7 |  |  |
| M-24 | Milestone: Final demo build tagged |  |  |  |  | Apr 8 | T5, T10, T15 |  |
| B-05 | Protected block before M-25 | Team | Apr 9 | Apr 14 | 4 d | Apr 14 |  |  |
| M-25 | Milestone: Senior Design Expo demo |  |  |  |  | Apr 15 | T5 |  |

Table 1. Fall dates are 2026; spring dates are 2027.

Critical path. T1 → T2 → T19 → T20 → T5. A slip on any of these moves M-23.

Risks. T6, T11, and T18 come first because they answer RK-01 to RK-03. M-19 and M-20 come before spring break for RK-08. Fall tasks are small because a course deliverable is due every week.

# 4. Table 2: Effort Matrix (Assignment #6)

Expected hours, (O + 4M + P) / 6. * = primary owner, who has the largest share.

| ID | Task | Grady | Brady | Briar | Dominic | Aiden | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| T1 | C1 app shell and guidance | 21.0* | 3.7 |  |  |  | 24.7 |
| T2 | C1 trip state machine | 23.2* |  | 2.9 | 2.9 |  | 29.0 |
| T3 | Configuration | 12.9* |  |  |  | 1.4 | 14.3 |
| T4 | Backend deployment on Render | 12.8* | 2.5 |  |  | 1.7 | 17.0 |
| T5 | End-to-end test drives | 18.8* | 3.1 | 3.1 | 3.1 | 3.1 | 31.3 |
| T6 | E2 no-retention + audio format |  |  | 10.7* |  |  | 10.7 |
| T7 | C2 I2 endpoint + transcription |  |  | 22.5* |  | 2.5 | 25.0 |
| T8 | C2 constraint extraction |  |  | 24.3* |  | 2.7 | 27.0 |
| T9 | C2 approval replies | 1.7 |  | 15.0* |  |  | 16.7 |
| T10 | C2 accent validation |  |  | 13.4* |  | 3.3 | 16.7 |
| T11 | E3 Maps terms + keys |  | 10.3* |  |  |  | 10.3 |
| T12 | C3 I4 endpoint + Maps client |  | 24.3* |  | 2.7 |  | 27.0 |
| T13 | C3 waypoint insertion |  | 24.3* |  | 2.7 |  | 27.0 |
| T14 | C3 preferences + next candidate | 1.9 | 16.8* |  |  |  | 18.7 |
| T15 | C3 edge-case tests |  | 12.2* |  | 2.1 |  | 14.3 |
| T16 | E4 weather thresholds |  |  |  | 10.7* |  | 10.7 |
| T17 | E4 client + rain scoring |  | 4.0 |  | 22.9* |  | 27.0 |
| T18 | C1 local mute + foreground service | 1.3 |  |  | 11.4* |  | 12.7 |
| T19 | C1 mic, mute, MuteError | 2.9 |  |  | 16.1* |  | 19.0 |
| T20 | Notifications | 1.7 |  |  | 15.0* |  | 16.7 |
| T21 | C4 schema + retention job |  |  |  |  | 14.3* | 14.3 |
| T22 | C4 checkQuota + recordUsage |  | 2.3 |  |  | 20.4* | 22.7 |
| T23 | Authentication | 2.9 |  |  |  | 16.1* | 19.0 |
| T24 | Logging |  | 1.0 |  |  | 9.3* | 10.3 |
| T25 | C4 report + caps |  |  |  |  | 14.3* | 14.3 |
|  | Total | 101.1 | 104.5 | 91.9 | 89.6 | 89.1 | 476.2 |
|  | Share | 21% | 22% | 19% | 19% | 19% | 100% |

Table 2. Effort matrix (hours).

Imbalance. Average is 95 hours. Brady is 10 percent over because he backs up most backend work. Dominic and Aiden are about 6 percent under. Briar is under on purpose (full-time job, RK-06).

Plan. Aiden takes Brady's support on T4 and Dominic takes Brady's support on T22 (5 hours). Then Brady is at 100 and everyone but Briar is within 6 percent. We log hours weekly and recheck at M-17 and M-20.

# 5. Work Breakdown Structure

| WBS ID | Phase or group | Tasks and milestones |
| --- | --- | --- |
| 1.0 | Design (complete) | M-01; M-02; M-03; M-04; M-05; M-06; M-07; M-08 |
| 2.0 | Research and Setup (Fall 2026) | T3 (Grady); T4 (Grady); T6 (Briar); T11 (Brady); T16 (Dominic); T18 (Dominic); T21 (Aiden) |
| 3.0 | Build (Spring 2027) | See 3.1 to 3.5 |
| 3.1 | C1 Mobile Navigation | T1 (Grady); T2 (Grady); T19 (Dominic) |
| 3.2 | C2 Speech Understanding | T7 (Briar); T8 (Briar); T9 (Briar) |
| 3.3 | C3 Route Planning (with E4) | T12 (Brady); T13 (Brady); T14 (Brady); T17 (Dominic) |
| 3.4 | C4 Usage Monitor | T22 (Aiden); T25 (Aiden) |
| 3.5 | Glue components | T20 (Dominic); T23 (Aiden); T24 (Aiden) |
| 4.0 | Test and Validation | T10 (Briar); T15 (Brady); T5 (Team) |
| 5.0 | Course deliverables and delivery | M-09; M-10; M-11; M-13; M-14; M-16; M-24; M-25 |

Diagram version: Figure2_WBS.drawio in the Planning folder.

# 6. Risk Register

| ID | Type | Risk | Likely | Impact | Strategy | Mitigation | Owner | Trigger | In Table 1 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RK-01 | External | OpenAI no-retention setting not confirmed (G-03). | Medium | High | Reduce | Do T6 first. Fallback: transcribe on the phone, send text only. | Briar | No answer by end of T6. | T6, T7 |
| RK-02 | External | Maps terms block in-app guidance (G-04). | Medium | High | Transfer | Do T11 before T1. Fallback: hand off to the Google Maps app. | Brady | T11 finds a blocking term. | T11, T1, T12 |
| RK-03 | Technical | Android pauses the mic, or voice mute is over 1 s (G-01, G-06). | Medium | High | Reduce | Prototype in T18. Foreground service; tap-only mute fallback. | Dominic | T18 mute over 1 s. | T18, T19, T20 |
| RK-04 | Technical | AI is slow or wrong, mainly with accents. | Medium | Medium | Reduce | Approval always required. Test in T10; tune prompts. | Briar | Under 8 of 10 at M-18. | T7, T8, T10 |
| RK-05 | External | API costs pass free credits. | Medium | Medium | Reduce | C4 caps before test drives; mocks in tests. | Aiden | Any budget hits 80 percent. | T4, T22, T25 |
| RK-06 | Team | Jobs limit hours (Briar full-time, Grady part-time). | High | Medium | Accept | Briar planned lighter; Aiden backs up C2 reviews. | Briar | A task slips over 3 days past buffer. | Table 2 |
| RK-07 | Team | Weekly course deliverables, exams, and breaks cut time. | High | Medium | Avoid | Fall tasks kept small; no work in breaks; protected blocks. | Grady | Task open on last day before a break. | B-01 to B-05 |
| RK-08 | Technical | C1, C2, C3 do not fit together. | Medium | High | Reduce | Build to D1 contracts with mocks; M-19 and M-20 before break. | Grady | M-19 or M-20 over 3 days late. | T2, T5, M-19, M-20 |
| RK-09 | External | No rain on test days (US-02). | High | Low | Accept | Replay recorded rain data. | Dominic | No rain day by start of T5. | T5, T16, T17 |